# Rough Order of Magnitude (ROM) Cost and Delivery Timeline

This section provides a rough order of magnitude (ROM) cost estimate and high-level delivery timeline for Bravent LLC’s proposed incremental replacement model for VA.gov. The ROM is provided for planning and market research purposes only and reflects Bravent’s experience modernizing large, mission-critical federal platforms while maintaining uninterrupted public access and continuous operations.

## 1.1 Scope Assumptions

- VA.gov replacement is executed as a multi-year, phased modernization effort, with legacy and replacement components operating in parallel.

- VA retains ownership of enterprise identity services, authoritative data sources, and policy decisions.

- Bravent delivers platform engineering, experience design, content and workflow modernization, DevSecOps, accessibility, security integration, and O&M.

- The approach supports millions of users, high availability, Section 508/WCAG 2.1 AA compliance, and federal security and privacy requirements.

- Modernization follows a portfolio-based platform architecture, enabling multiple VA business lines to transition independently.

## 1.2 Order of Magnitude Cost Overview

| Period | Estimated ROM |
| --- | --- |
| Year 1 – Planning & Pilot Replacement | $5.0M – $8.0M |
| Year 2 – Scaled Portfolio Replacement | $8.0M – $14.0M |
| Year 3 – Expanded Replacement & Optimization | $6.0M – $10.0M |
| Steady-State O&M (Annual) | $3.0M – $5.0M |

Estimated 3-Year ROM Total: $19.0M – $32.0M

These estimates reflect a blended multidisciplinary team supporting design, engineering, content transformation, accessibility, security, DevSecOps, and operations across a national-scale digital platform.

## 1.3 Phased Timeline and Key Milestones

### Phase 0 – Program Mobilization (Months 0–2)

### Contract kickoff and governance setup

### Security onboarding and environment access

### DevSecOps pipelines, monitoring, and reporting established

### Phase 1 – Replacement Planning and Pilot Capabilities (Months 3–9)

### Mapping of VA.gov architecture, content domains, and workflows

### Selection and deployment of pilot replacement components

### Parallel operation with legacy VA.gov

### Initial accessibility-validated user journeys and metrics

### Phase 2 – Incremental Portfolio Replacement (Months 10–24)

- Expansion of replacement platform across multiple VA.gov portfolios

- Incremental migration of content, workflows, and user journeys

- Preservation of public access, URLs, and continuity of service

- Shared platform services for security, compliance, and analytics

### Phase 3 – Optimization and Legacy Retirement (Months 25–36)

### Performance, resilience, and security hardening

### Systematic retirement of legacy VA.gov components

### Establishment of steady-state operating model

### Phase 4 – Steady-State Operations (Year 4+)

- Ongoing operations, maintenance, and enhancements

- Continuous accessibility, compliance, and security monitoring

- Incremental modernization based on usage and Veteran feedback

## 1.4 Value to VA

This ROM and timeline reflect a risk-managed, incremental replacement strategy that avoids a single “big bang” transition. The approach enables VA to deliver early improvements, reduce operational risk, preserve public trust, and modernize VA.gov in a controlled, measurable, and Veteran-centered manner while maintaining continuous access to mission-critical services.